## Schedule
activity_id | activity_name | category | planned_start | planned_end | planned_duration_days | predecessor | status | planned_quantity_percent | current_actual_percent | unit | project_id | data_type
F01-A001 | Site Office Setup - Phase 3 | Site | 2026-08-15 | 2026-08-26 | 12 | — | Not Started | 100 | 0 | m | INFRA-01 | synthetic_demo_data
F01-A002 | Quality Concrete Slump Testing - South Section | Quality | 2026-08-26 | 2026-08-27 | 2 | F01-A001 | In Progress | 100 | 32 | Nos | INFRA-01 | synthetic_demo_data
F01-A003 | Site Welfare Facility Setup - Chainage 500-1000 | Site | 2026-08-22 | 2026-08-24 | 3 | F01-A001 | Not Started | 100 | 0 | m | INFRA-01 | synthetic_demo_data
F01-A004 | Site Inspection - Zone C | Site | 2026-09-14 | 2026-09-18 | 5 | F01-A001 | Not Started | 100 | 0 | Nos | INFRA-01 | synthetic_demo_data
F01-A005 | Road Signboard Installation - East Section | Road | 2026-08-19 | 2026-08-19 | 1 | F01-A001 | Completed | 100 | 98 | Nos | INFRA-01 | synthetic_demo_data
F01-A006 | Rehabilitation Concrete Rehabilitation - Zone B | Rehabilitation | 2026-08-22 | 2026-08-23 | 2 | F01-A004 | Completed | 100 | 96 | m | INFRA-01 | synthetic_demo_data
F01-A007 | Finishing Waterproofing Membrane - Zone B | Finishing | 2026-08-21 | 2026-08-29 | 9 | F01-A004 | Completed | 100 | 100 | m² | INFRA-01 | synthetic_demo_data
F01-A008 | Rehabilitation Existing Road Resurfacing - Package 3 | Rehabilitation | 2026-09-01 | 2026-09-14 | 14 | F01-A001 | In Progress | 100 | 40 | m | INFRA-01 | synthetic_demo_data
F01-A009 | Site Demobilization - Zone C | Site | 2026-08-25 | 2026-09-02 | 9 | F01-A007 | At Risk | 100 | 32 | m | INFRA-01 | synthetic_demo_data
F01-A010 | Safety Pedestrian Diversion - West Section | Safety | 2026-08-12 | 2026-08-13 | 2 | F01-A009 | Completed | 100 | 100 | m | INFRA-01 | synthetic_demo_data
F01-A011 | Quality Material Inspection - Phase 3 | Quality | 2026-08-16 | 2026-08-28 | 13 | F01-A006 | Completed | 100 | 96 | Nos | INFRA-01 | synthetic_demo_data
F01-A012 | Drainage Flow Testing - Zone A | Drainage | 2026-09-15 | 2026-09-18 | 4 | F01-A005 | In Progress | 100 | 49 | Nos | INFRA-01 | synthetic_demo_data
F01-A013 | Landscaping Lawn Preparation - Zone C | Landscaping | 2026-09-13 | 2026-09-17 | 5 | F01-A010 | Completed | 100 | 100 | m | INFRA-01 | synthetic_demo_data
F01-A014 | Safety Toolbox Talk - North Section | Safety | 2026-09-02 | 2026-09-15 | 14 | F01-A011 | In Progress | 100 | 79 | Nos | INFRA-01 | synthetic_demo_data
F01-A015 | Road Paver Block Installation - Zone C | Road | 2026-08-20 | 2026-08-20 | 1 | F01-A006 | Completed | 100 | 98 | Nos | INFRA-01 | synthetic_demo_data
F01-A016 | Utility Water Pipeline Disinfection - Chainage 0-500 | Utility | 2026-08-20 | 2026-09-02 | 14 | F01-A014 | In Progress | 100 | 58 | m | INFRA-01 | synthetic_demo_data
F01-A017 | Drainage Pipe Joint Testing - Package 2 | Drainage | 2026-09-07 | 2026-09-19 | 13 | F01-A009 | In Progress | 100 | 90 | Nos | INFRA-01 | synthetic_demo_data
F01-A018 | Structural Column Reinforcement - Package 2 | Structural | 2026-08-10 | 2026-08-22 | 13 | F01-A010 | Completed | 100 | 98 | m | INFRA-01 | synthetic_demo_data
F01-A019 | Structural Slab Formwork - Phase 2 | Structural | 2026-08-10 | 2026-08-12 | 3 | F01-A009 | In Progress | 100 | 63 | m | INFRA-01 | synthetic_demo_data
F01-A020 | Quality Interim Work Inspection - South Section | Quality | 2026-08-29 | 2026-09-09 | 12 | F01-A008 | At Risk | 100 | 44 | Nos | INFRA-01 | synthetic_demo_data
F01-A021 | Utility Sewer Pipeline Trenching - Package 1 | Utility | 2026-08-21 | 2026-08-28 | 8 | F01-A017 | Completed | 100 | 99 | m | INFRA-01 | synthetic_demo_data
F01-A022 | Structural Retaining Wall Reinforcement - North Section | Structural | 2026-08-08 | 2026-08-17 | 10 | F01-A016 | In Progress | 100 | 33 | m | INFRA-01 | synthetic_demo_data
F01-A023 | Finishing Plastering - East Section | Finishing | 2026-08-16 | 2026-08-29 | 14 | F01-A013 | In Progress | 100 | 82 | m² | INFRA-01 | synthetic_demo_data
F01-A024 | Utility Utility Chamber Construction - Package 3 | Utility | 2026-08-10 | 2026-08-14 | 5 | F01-A014 | In Progress | 100 | 54 | m | INFRA-01 | synthetic_demo_data
F01-A025 | Road Road Marking - West Section | Road | 2026-08-23 | 2026-08-26 | 4 | F01-A002 | In Progress | 100 | 64 | m | INFRA-01 | synthetic_demo_data
F01-A026 | Quality Pipeline CCTV Inspection - Zone C | Quality | 2026-08-18 | 2026-08-19 | 2 | F01-A003 | In Progress | 100 | 65 | Nos | INFRA-01 | synthetic_demo_data
F01-A027 | Site Mobilization - Package 1 | Site | 2026-09-12 | 2026-09-20 | 9 | F01-A012 | In Progress | 100 | 56 | m | INFRA-01 | synthetic_demo_data
F01-A028 | Site Clearance - Chainage 0-500 | Site | 2026-08-08 | 2026-08-16 | 9 | F01-A018 | Completed | 100 | 100 | m | INFRA-01 | synthetic_demo_data
F01-A029 | Finishing Exterior Painting - Phase 3 | Finishing | 2026-09-04 | 2026-09-13 | 10 | F01-A011 | Completed | 100 | 97 | m² | INFRA-01 | synthetic_demo_data
F01-A030 | Rehabilitation Existing Road Resurfacing - Phase 1 | Rehabilitation | 2026-09-09 | 2026-09-14 | 6 | F01-A002 | In Progress | 100 | 64 | m | INFRA-01 | synthetic_demo_data

## Data_Dictionary
field | description
activity_id | Unique activity ID
activity_name | Activity name
category | Work category
planned_start | Planned start date
planned_end | Planned finish date
planned_duration_days | Planned duration in days
predecessor | Predecessor activity ID
status | Current schedule status
planned_quantity_percent | Planned completion percentage
current_actual_percent | Current actual completion percentage
unit | Quantity unit
project_id | Synthetic project ID
data_type | Dataset marker