## Schedule
activity_id | activity_name | category | planned_start | planned_end | planned_duration_days | predecessor | status | planned_quantity_percent | current_actual_percent | unit | project_id | data_type
F02-A001 | Finishing Metal Railing Installation - Package 3 | Finishing | 2026-08-10 | 2026-08-13 | 4 | — | At Risk | 100 | 19 | Nos | INFRA-02 | synthetic_demo_data
F02-A002 | Earthwork Final Level Preparation - Package 2 | Earthwork | 2026-08-11 | 2026-08-23 | 13 | F02-A001 | In Progress | 100 | 72 | m | INFRA-02 | synthetic_demo_data
F02-A003 | Safety Temporary Shoring Installation - Zone A | Safety | 2026-09-07 | 2026-09-15 | 9 | F02-A002 | In Progress | 100 | 84 | Nos | INFRA-02 | synthetic_demo_data
F02-A004 | Finishing Floor Screed Installation - Chainage 500-1000 | Finishing | 2026-09-13 | 2026-09-19 | 7 | F02-A002 | In Progress | 100 | 23 | Nos | INFRA-02 | synthetic_demo_data
F02-A005 | Electrical Conduit Installation - Chainage 500-1000 | Electrical | 2026-08-15 | 2026-08-16 | 2 | F02-A004 | In Progress | 100 | 55 | Nos | INFRA-02 | synthetic_demo_data
F02-A006 | Drainage RCC Drain Construction - West Section | Drainage | 2026-09-17 | 2026-09-24 | 8 | F02-A005 | Not Started | 100 | 0 | m | INFRA-02 | synthetic_demo_data
F02-A007 | Drainage Trench Excavation - Package 2 | Drainage | 2026-08-23 | 2026-08-27 | 5 | F02-A004 | In Progress | 100 | 84 | m³ | INFRA-02 | synthetic_demo_data
F02-A008 | Rehabilitation Pothole Repair - Zone B | Rehabilitation | 2026-09-13 | 2026-09-18 | 6 | F02-A007 | Completed | 100 | 97 | m | INFRA-02 | synthetic_demo_data
F02-A009 | Site Temporary Lighting - South Section | Site | 2026-08-19 | 2026-08-25 | 7 | F02-A006 | At Risk | 100 | 64 | m | INFRA-02 | synthetic_demo_data
F02-A010 | Rehabilitation Existing Pavement Milling - Phase 2 | Rehabilitation | 2026-08-21 | 2026-08-28 | 8 | F02-A006 | In Progress | 100 | 19 | m² | INFRA-02 | synthetic_demo_data
F02-A011 | Drainage Pipe Laying - Package 2 | Drainage | 2026-08-29 | 2026-09-03 | 6 | F02-A008 | In Progress | 100 | 73 | m | INFRA-02 | synthetic_demo_data
F02-A012 | Earthwork Excavation - Chainage 500-1000 | Earthwork | 2026-09-09 | 2026-09-09 | 1 | F02-A010 | Completed | 100 | 96 | m³ | INFRA-02 | synthetic_demo_data
F02-A013 | Finishing Handrail Installation - Package 1 | Finishing | 2026-08-08 | 2026-08-16 | 9 | F02-A002 | Completed | 100 | 98 | Nos | INFRA-02 | synthetic_demo_data
F02-A014 | Structural Steel Structure Erection - Package 3 | Structural | 2026-08-09 | 2026-08-12 | 4 | F02-A012 | Completed | 100 | 96 | m | INFRA-02 | synthetic_demo_data
F02-A015 | Utility Water Valve Chamber Construction - Chainage 0-500 | Utility | 2026-08-06 | 2026-08-18 | 13 | F02-A001 | At Risk | 100 | 57 | m | INFRA-02 | synthetic_demo_data
F02-A016 | Utility Water Pipeline Jointing - Zone B | Utility | 2026-09-18 | 2026-09-28 | 11 | F02-A004 | Completed | 100 | 99 | m | INFRA-02 | synthetic_demo_data
F02-A017 | Electrical Conduit Installation - Package 3 | Electrical | 2026-08-14 | 2026-08-16 | 3 | F02-A008 | Not Started | 100 | 0 | Nos | INFRA-02 | synthetic_demo_data
F02-A018 | Quality Pre-Construction Inspection - Chainage 500-1000 | Quality | 2026-08-31 | 2026-08-31 | 1 | F02-A005 | In Progress | 100 | 90 | Nos | INFRA-02 | synthetic_demo_data
F02-A019 | Road Dense Bituminous Macadam - Phase 1 | Road | 2026-08-25 | 2026-09-05 | 12 | F02-A006 | In Progress | 100 | 43 | m | INFRA-02 | synthetic_demo_data
F02-A020 | Site Fencing - Chainage 500-1000 | Site | 2026-08-07 | 2026-08-19 | 13 | F02-A009 | Not Started | 100 | 0 | m | INFRA-02 | synthetic_demo_data
F02-A021 | Road Dense Bituminous Macadam - Chainage 500-1000 | Road | 2026-08-20 | 2026-08-26 | 7 | F02-A001 | In Progress | 100 | 44 | m | INFRA-02 | synthetic_demo_data
F02-A022 | Electrical Cable Tray Installation - North Section | Electrical | 2026-08-05 | 2026-08-12 | 8 | F02-A020 | In Progress | 100 | 86 | Nos | INFRA-02 | synthetic_demo_data
F02-A023 | Finishing Plastering - Chainage 0-500 | Finishing | 2026-08-23 | 2026-08-25 | 3 | F02-A022 | Completed | 100 | 100 | m² | INFRA-02 | synthetic_demo_data
F02-A024 | Drainage Catchpit Construction - Chainage 0-500 | Drainage | 2026-09-03 | 2026-09-06 | 4 | F02-A011 | In Progress | 100 | 57 | m | INFRA-02 | synthetic_demo_data
F02-A025 | Road Kerb Laying - East Section | Road | 2026-08-28 | 2026-09-03 | 7 | F02-A010 | Completed | 100 | 96 | m | INFRA-02 | synthetic_demo_data
F02-A026 | Utility Utility Duct Installation - Zone A | Utility | 2026-09-17 | 2026-09-17 | 1 | F02-A009 | In Progress | 100 | 44 | Nos | INFRA-02 | synthetic_demo_data
F02-A027 | Electrical Earthing Installation - Chainage 0-500 | Electrical | 2026-09-01 | 2026-09-06 | 6 | F02-A025 | In Progress | 100 | 23 | Nos | INFRA-02 | synthetic_demo_data
F02-A028 | Structural Beam Formwork - South Section | Structural | 2026-08-10 | 2026-08-10 | 1 | F02-A001 | In Progress | 100 | 60 | m | INFRA-02 | synthetic_demo_data
F02-A029 | Structural Steel Structure Erection - Chainage 0-500 | Structural | 2026-09-17 | 2026-09-29 | 13 | F02-A005 | In Progress | 100 | 40 | m | INFRA-02 | synthetic_demo_data
F02-A030 | Finishing Wall Tile Installation - Zone A | Finishing | 2026-09-13 | 2026-09-18 | 6 | F02-A011 | In Progress | 100 | 80 | Nos | INFRA-02 | synthetic_demo_data

## Data_Dictionary
field | description
activity_id | Unique activity ID
activity_name | Activity name
category | Work category
planned_start | Planned start date
planned_end | Planned finish date
planned_duration_days | Planned duration in days
predecessor | Predecessor activity ID
status | Current schedule status
planned_quantity_percent | Planned completion percentage
current_actual_percent | Current actual completion percentage
unit | Quantity unit
project_id | Synthetic project ID
data_type | Dataset marker