## Schedule
activity_id | activity_name | category | planned_start | planned_end | planned_duration_days | predecessor | status | planned_quantity_percent | current_actual_percent | unit | project_id | data_type
F03-A001 | Rehabilitation Existing Culvert Rehabilitation - Zone C | Rehabilitation | 2026-09-04 | 2026-09-17 | 14 | — | Not Started | 100 | 0 | m | INFRA-03 | synthetic_demo_data
F03-A002 | Demolition Existing Fence Removal - East Section | Demolition | 2026-08-10 | 2026-08-14 | 5 | F03-A001 | Completed | 100 | 100 | m | INFRA-03 | synthetic_demo_data
F03-A003 | Utility Water Pipeline Jointing - Zone A | Utility | 2026-09-05 | 2026-09-11 | 7 | F03-A002 | Not Started | 100 | 0 | m | INFRA-03 | synthetic_demo_data
F03-A004 | Site Material Testing Area Setup - South Section | Site | 2026-09-15 | 2026-09-20 | 6 | F03-A001 | In Progress | 100 | 25 | Nos | INFRA-03 | synthetic_demo_data
F03-A005 | Road Paver Block Installation - Zone A | Road | 2026-08-21 | 2026-08-23 | 3 | F03-A001 | Completed | 100 | 99 | Nos | INFRA-03 | synthetic_demo_data
F03-A006 | Road Traffic Island Construction - South Section | Road | 2026-09-07 | 2026-09-15 | 9 | F03-A001 | Completed | 100 | 99 | m | INFRA-03 | synthetic_demo_data
F03-A007 | Site Grading - East Section | Site | 2026-09-08 | 2026-09-19 | 12 | F03-A005 | Not Started | 100 | 0 | m² | INFRA-03 | synthetic_demo_data
F03-A008 | Finishing Wall Tile Installation - Package 1 | Finishing | 2026-08-25 | 2026-08-30 | 6 | F03-A003 | At Risk | 100 | 48 | Nos | INFRA-03 | synthetic_demo_data
F03-A009 | Landscaping Shrub Plantation - North Section | Landscaping | 2026-09-16 | 2026-09-17 | 2 | F03-A001 | At Risk | 100 | 44 | Nos | INFRA-03 | synthetic_demo_data
F03-A010 | Earthwork Formation Preparation - West Section | Earthwork | 2026-09-08 | 2026-09-16 | 9 | F03-A005 | Completed | 100 | 97 | m | INFRA-03 | synthetic_demo_data
F03-A011 | Finishing Masonry Wall Construction - Chainage 500-1000 | Finishing | 2026-08-22 | 2026-09-01 | 11 | F03-A001 | In Progress | 100 | 71 | m | INFRA-03 | synthetic_demo_data
F03-A012 | Road Shoulder Construction - Package 2 | Road | 2026-09-09 | 2026-09-14 | 6 | F03-A001 | Completed | 100 | 99 | m | INFRA-03 | synthetic_demo_data
F03-A013 | Site Office Setup - Package 2 | Site | 2026-09-16 | 2026-09-16 | 1 | F03-A008 | Not Started | 100 | 0 | m | INFRA-03 | synthetic_demo_data
F03-A014 | Road Median Construction - Package 2 | Road | 2026-09-16 | 2026-09-29 | 14 | F03-A001 | Completed | 100 | 99 | m | INFRA-03 | synthetic_demo_data
F03-A015 | Structural Column Formwork - Package 3 | Structural | 2026-08-29 | 2026-09-10 | 13 | F03-A009 | In Progress | 100 | 20 | m | INFRA-03 | synthetic_demo_data
F03-A016 | Foundation Anchor Bolt Installation - Phase 1 | Foundation | 2026-09-18 | 2026-09-24 | 7 | F03-A007 | Completed | 100 | 99 | Nos | INFRA-03 | synthetic_demo_data
F03-A017 | Finishing Floor Screed Installation - Zone A | Finishing | 2026-09-13 | 2026-09-13 | 1 | F03-A011 | In Progress | 100 | 62 | Nos | INFRA-03 | synthetic_demo_data
F03-A018 | Road Signboard Installation - Zone B | Road | 2026-08-16 | 2026-08-24 | 9 | F03-A011 | In Progress | 100 | 72 | Nos | INFRA-03 | synthetic_demo_data
F03-A019 | Landscaping Shrub Plantation - East Section | Landscaping | 2026-09-10 | 2026-09-12 | 3 | F03-A004 | Not Started | 100 | 0 | Nos | INFRA-03 | synthetic_demo_data
F03-A020 | Road Junction Improvement - North Section | Road | 2026-08-27 | 2026-09-06 | 11 | F03-A017 | Not Started | 100 | 0 | m | INFRA-03 | synthetic_demo_data
F03-A021 | Finishing External Plaster Finishing - North Section | Finishing | 2026-09-17 | 2026-09-25 | 9 | F03-A003 | In Progress | 100 | 41 | m² | INFRA-03 | synthetic_demo_data
F03-A022 | Quality Workfront Handover Inspection - Phase 2 | Quality | 2026-08-26 | 2026-09-05 | 11 | F03-A021 | In Progress | 100 | 77 | Nos | INFRA-03 | synthetic_demo_data
F03-A023 | Foundation Reinforcement - North Section | Foundation | 2026-09-18 | 2026-09-20 | 3 | F03-A013 | Completed | 100 | 98 | m | INFRA-03 | synthetic_demo_data
F03-A024 | Structural Steel Member Fabrication - Package 1 | Structural | 2026-09-13 | 2026-09-25 | 13 | F03-A003 | In Progress | 100 | 23 | m | INFRA-03 | synthetic_demo_data
F03-A025 | Rehabilitation Existing Pavement Milling - Package 3 | Rehabilitation | 2026-09-13 | 2026-09-14 | 2 | F03-A008 | In Progress | 100 | 77 | m² | INFRA-03 | synthetic_demo_data
F03-A026 | Landscaping Lawn Preparation - Package 1 | Landscaping | 2026-08-13 | 2026-08-24 | 12 | F03-A011 | At Risk | 100 | 76 | m | INFRA-03 | synthetic_demo_data
F03-A027 | Finishing Metal Railing Installation - Package 1 | Finishing | 2026-08-12 | 2026-08-25 | 14 | F03-A026 | Not Started | 100 | 0 | Nos | INFRA-03 | synthetic_demo_data
F03-A028 | Site Welfare Facility Setup - South Section | Site | 2026-09-14 | 2026-09-24 | 11 | F03-A008 | Not Started | 100 | 0 | m | INFRA-03 | synthetic_demo_data
F03-A029 | Quality Material Inspection - Phase 2 | Quality | 2026-08-25 | 2026-08-27 | 3 | F03-A001 | Completed | 100 | 100 | Nos | INFRA-03 | synthetic_demo_data
F03-A030 | Foundation Pile Integrity Testing - Zone C | Foundation | 2026-08-21 | 2026-09-03 | 14 | F03-A003 | Completed | 100 | 99 | Nos | INFRA-03 | synthetic_demo_data

## Data_Dictionary
field | description
activity_id | Unique activity ID
activity_name | Activity name
category | Work category
planned_start | Planned start date
planned_end | Planned finish date
planned_duration_days | Planned duration in days
predecessor | Predecessor activity ID
status | Current schedule status
planned_quantity_percent | Planned completion percentage
current_actual_percent | Current actual completion percentage
unit | Quantity unit
project_id | Synthetic project ID
data_type | Dataset marker