## Schedule
activity_id | activity_name | category | planned_start | planned_end | planned_duration_days | predecessor | status | planned_quantity_percent | current_actual_percent | unit | project_id | data_type
F04-A001 | Earthwork Grading - Zone A | Earthwork | 2026-09-22 | 2026-10-04 | 13 | — | At Risk | 100 | 30 | m² | INFRA-04 | synthetic_demo_data
F04-A002 | Landscaping Irrigation Line Installation - Package 3 | Landscaping | 2026-08-11 | 2026-08-11 | 1 | F04-A001 | In Progress | 100 | 45 | Nos | INFRA-04 | synthetic_demo_data
F04-A003 | Utility Sewer Pipeline Testing - Zone A | Utility | 2026-08-16 | 2026-08-27 | 12 | F04-A002 | In Progress | 100 | 28 | Nos | INFRA-04 | synthetic_demo_data
F04-A004 | Road Kerb Laying - West Section | Road | 2026-09-17 | 2026-09-27 | 11 | F04-A002 | In Progress | 100 | 39 | m | INFRA-04 | synthetic_demo_data
F04-A005 | Rehabilitation Existing Culvert Rehabilitation - South Section | Rehabilitation | 2026-09-10 | 2026-09-10 | 1 | F04-A001 | Completed | 100 | 96 | m | INFRA-04 | synthetic_demo_data
F04-A006 | Electrical Generator Cable Connection - Package 2 | Electrical | 2026-08-18 | 2026-08-29 | 12 | F04-A005 | Completed | 100 | 96 | m | INFRA-04 | synthetic_demo_data
F04-A007 | Earthwork Formation Preparation - North Section | Earthwork | 2026-08-24 | 2026-09-02 | 10 | F04-A004 | In Progress | 100 | 23 | m | INFRA-04 | synthetic_demo_data
F04-A008 | Utility Water Line Relocation - North Section | Utility | 2026-08-31 | 2026-09-03 | 4 | F04-A006 | In Progress | 100 | 65 | m | INFRA-04 | synthetic_demo_data
F04-A009 | Road Reflector Installation - Chainage 500-1000 | Road | 2026-09-20 | 2026-09-24 | 5 | F04-A007 | Not Started | 100 | 0 | Nos | INFRA-04 | synthetic_demo_data
F04-A010 | Road Reflector Installation - Zone C | Road | 2026-09-10 | 2026-09-14 | 5 | F04-A008 | At Risk | 100 | 15 | Nos | INFRA-04 | synthetic_demo_data
F04-A011 | Site Mobilization - Phase 2 | Site | 2026-08-13 | 2026-08-22 | 10 | F04-A007 | Completed | 100 | 99 | m | INFRA-04 | synthetic_demo_data
F04-A012 | Finishing Final Cleaning - South Section | Finishing | 2026-09-14 | 2026-09-26 | 13 | F04-A007 | Not Started | 100 | 0 | m | INFRA-04 | synthetic_demo_data
F04-A013 | Site Demobilization - East Section | Site | 2026-09-17 | 2026-09-30 | 14 | F04-A005 | At Risk | 100 | 45 | m | INFRA-04 | synthetic_demo_data
F04-A014 | Drainage Inlet Construction - East Section | Drainage | 2026-08-11 | 2026-08-11 | 1 | F04-A013 | Completed | 100 | 99 | m | INFRA-04 | synthetic_demo_data
F04-A015 | Utility Service Restoration - Phase 2 | Utility | 2026-08-16 | 2026-08-21 | 6 | F04-A010 | Not Started | 100 | 0 | m | INFRA-04 | synthetic_demo_data
F04-A016 | Site Office Setup - Chainage 0-500 | Site | 2026-08-25 | 2026-09-02 | 9 | F04-A003 | In Progress | 100 | 76 | m | INFRA-04 | synthetic_demo_data
F04-A017 | Rehabilitation Existing Manhole Reconstruction - Zone A | Rehabilitation | 2026-09-11 | 2026-09-14 | 4 | F04-A011 | Completed | 100 | 100 | m | INFRA-04 | synthetic_demo_data
F04-A018 | Drainage Catchpit Construction - South Section | Drainage | 2026-09-06 | 2026-09-14 | 9 | F04-A006 | Not Started | 100 | 0 | m | INFRA-04 | synthetic_demo_data
F04-A019 | Rehabilitation Existing Culvert Rehabilitation - Zone A | Rehabilitation | 2026-09-10 | 2026-09-15 | 6 | F04-A015 | In Progress | 100 | 75 | m | INFRA-04 | synthetic_demo_data
F04-A020 | Rehabilitation Existing Culvert Rehabilitation - Phase 1 | Rehabilitation | 2026-08-29 | 2026-09-05 | 8 | F04-A002 | Completed | 100 | 97 | m | INFRA-04 | synthetic_demo_data
F04-A021 | Electrical Control Panel Installation - Zone C | Electrical | 2026-08-22 | 2026-09-03 | 13 | F04-A011 | Not Started | 100 | 0 | Nos | INFRA-04 | synthetic_demo_data
F04-A022 | Foundation Pile Bore Excavation - Zone C | Foundation | 2026-09-09 | 2026-09-09 | 1 | F04-A020 | In Progress | 100 | 44 | m³ | INFRA-04 | synthetic_demo_data
F04-A023 | Electrical Insulation Testing - Phase 2 | Electrical | 2026-09-23 | 2026-10-06 | 14 | F04-A013 | Completed | 100 | 97 | Nos | INFRA-04 | synthetic_demo_data
F04-A024 | Earthwork Cut and Fill Balancing - Zone A | Earthwork | 2026-08-10 | 2026-08-20 | 11 | F04-A002 | Completed | 100 | 98 | m | INFRA-04 | synthetic_demo_data
F04-A025 | Drainage Headwall Construction - Zone B | Drainage | 2026-08-16 | 2026-08-21 | 6 | F04-A023 | In Progress | 100 | 44 | m | INFRA-04 | synthetic_demo_data
F04-A026 | Structural Beam Formwork - Zone B | Structural | 2026-09-18 | 2026-09-18 | 1 | F04-A020 | In Progress | 100 | 68 | m | INFRA-04 | synthetic_demo_data
F04-A027 | Finishing Blockwork Construction - Package 2 | Finishing | 2026-08-31 | 2026-09-06 | 7 | F04-A022 | In Progress | 100 | 80 | m | INFRA-04 | synthetic_demo_data
F04-A028 | Utility Sewer Pipeline Testing - Package 3 | Utility | 2026-08-29 | 2026-08-31 | 3 | F04-A002 | In Progress | 100 | 46 | Nos | INFRA-04 | synthetic_demo_data
F04-A029 | Rehabilitation Existing Culvert Rehabilitation - East Section | Rehabilitation | 2026-08-18 | 2026-08-27 | 10 | F04-A005 | At Risk | 100 | 43 | m | INFRA-04 | synthetic_demo_data
F04-A030 | Finishing Floor Tile Installation - North Section | Finishing | 2026-09-06 | 2026-09-15 | 10 | F04-A026 | In Progress | 100 | 29 | Nos | INFRA-04 | synthetic_demo_data

## Data_Dictionary
field | description
activity_id | Unique activity ID
activity_name | Activity name
category | Work category
planned_start | Planned start date
planned_end | Planned finish date
planned_duration_days | Planned duration in days
predecessor | Predecessor activity ID
status | Current schedule status
planned_quantity_percent | Planned completion percentage
current_actual_percent | Current actual completion percentage
unit | Quantity unit
project_id | Synthetic project ID
data_type | Dataset marker