## Schedule
activity_id | activity_name | category | planned_start | planned_end | planned_duration_days | predecessor | status | planned_quantity_percent | current_actual_percent | unit | project_id | data_type
F06-A001 | Quality Weld Inspection - Zone B | Quality | 2026-08-23 | 2026-08-29 | 7 | — | Completed | 100 | 97 | Nos | INFRA-06 | synthetic_demo_data
F06-A002 | Site Demobilization - Chainage 0-500 | Site | 2026-09-03 | 2026-09-16 | 14 | F06-A001 | In Progress | 100 | 26 | m | INFRA-06 | synthetic_demo_data
F06-A003 | Structural Protective Painting - Phase 3 | Structural | 2026-09-05 | 2026-09-17 | 13 | F06-A002 | Completed | 100 | 99 | m² | INFRA-06 | synthetic_demo_data
F06-A004 | Site Preparation - South Section | Site | 2026-09-20 | 2026-09-22 | 3 | F06-A001 | Completed | 100 | 96 | m | INFRA-06 | synthetic_demo_data
F06-A005 | Site Traffic Access Setup - Package 3 | Site | 2026-08-21 | 2026-08-21 | 1 | F06-A003 | At Risk | 100 | 84 | m | INFRA-06 | synthetic_demo_data
F06-A006 | Drainage Manhole Construction - Phase 1 | Drainage | 2026-08-30 | 2026-09-08 | 10 | F06-A005 | Completed | 100 | 100 | m | INFRA-06 | synthetic_demo_data
F06-A007 | Utility Water Pressure Testing - South Section | Utility | 2026-08-21 | 2026-08-28 | 8 | F06-A003 | In Progress | 100 | 80 | Nos | INFRA-06 | synthetic_demo_data
F06-A008 | Electrical Streetlight Pole Installation - North Section | Electrical | 2026-09-17 | 2026-09-24 | 8 | F06-A003 | Completed | 100 | 98 | Nos | INFRA-06 | synthetic_demo_data
F06-A009 | Earthwork Surplus Soil Disposal - South Section | Earthwork | 2026-08-15 | 2026-08-28 | 14 | F06-A006 | In Progress | 100 | 48 | m³ | INFRA-06 | synthetic_demo_data
F06-A010 | Utility Sewer Manhole Construction - North Section | Utility | 2026-08-29 | 2026-09-03 | 6 | F06-A003 | In Progress | 100 | 69 | m | INFRA-06 | synthetic_demo_data
F06-A011 | Structural Slab Formwork - West Section | Structural | 2026-08-25 | 2026-09-07 | 14 | F06-A009 | In Progress | 100 | 76 | m | INFRA-06 | synthetic_demo_data
F06-A012 | Structural Slab Reinforcement - Chainage 500-1000 | Structural | 2026-08-17 | 2026-08-28 | 12 | F06-A001 | Completed | 100 | 100 | m | INFRA-06 | synthetic_demo_data
F06-A013 | Site Clearance - South Section | Site | 2026-09-06 | 2026-09-19 | 14 | F06-A006 | Completed | 100 | 96 | m | INFRA-06 | synthetic_demo_data
F06-A014 | Demolition Existing Lighting Removal - Chainage 0-500 | Demolition | 2026-09-04 | 2026-09-12 | 9 | F06-A012 | In Progress | 100 | 85 | m | INFRA-06 | synthetic_demo_data
F06-A015 | Quality Pipeline CCTV Inspection - Package 3 | Quality | 2026-08-23 | 2026-09-01 | 10 | F06-A005 | At Risk | 100 | 34 | Nos | INFRA-06 | synthetic_demo_data
F06-A016 | Safety Traffic Diversion - Phase 3 | Safety | 2026-09-03 | 2026-09-15 | 13 | F06-A015 | At Risk | 100 | 29 | m | INFRA-06 | synthetic_demo_data
F06-A017 | Foundation Formwork - Package 1 | Foundation | 2026-09-20 | 2026-09-25 | 6 | F06-A009 | Not Started | 100 | 0 | m | INFRA-06 | synthetic_demo_data
F06-A018 | Road Signboard Installation - South Section | Road | 2026-09-22 | 2026-10-04 | 13 | F06-A008 | Not Started | 100 | 0 | Nos | INFRA-06 | synthetic_demo_data
F06-A019 | Site Temporary Lighting - North Section | Site | 2026-09-12 | 2026-09-13 | 2 | F06-A017 | In Progress | 100 | 60 | m | INFRA-06 | synthetic_demo_data
F06-A020 | Structural Retaining Wall Concreting - Chainage 0-500 | Structural | 2026-08-17 | 2026-08-18 | 2 | F06-A015 | In Progress | 100 | 43 | m³ | INFRA-06 | synthetic_demo_data
F06-A021 | Foundation Pedestal Concreting - South Section | Foundation | 2026-09-18 | 2026-09-18 | 1 | F06-A018 | In Progress | 100 | 84 | m³ | INFRA-06 | synthetic_demo_data
F06-A022 | Structural Expansion Joint Installation - Phase 2 | Structural | 2026-09-15 | 2026-09-24 | 10 | F06-A009 | At Risk | 100 | 30 | Nos | INFRA-06 | synthetic_demo_data
F06-A023 | Rehabilitation Concrete Rehabilitation - Package 1 | Rehabilitation | 2026-08-24 | 2026-09-03 | 11 | F06-A005 | Completed | 100 | 96 | m | INFRA-06 | synthetic_demo_data
F06-A024 | Landscaping Turf Installation - Chainage 500-1000 | Landscaping | 2026-09-27 | 2026-10-10 | 14 | F06-A018 | In Progress | 100 | 27 | Nos | INFRA-06 | synthetic_demo_data
F06-A025 | Earthwork Soil Replacement - Chainage 500-1000 | Earthwork | 2026-08-26 | 2026-08-29 | 4 | F06-A014 | In Progress | 100 | 37 | m³ | INFRA-06 | synthetic_demo_data
F06-A026 | Road Footpath Tile Laying - East Section | Road | 2026-09-10 | 2026-09-16 | 7 | F06-A001 | Not Started | 100 | 0 | m | INFRA-06 | synthetic_demo_data
F06-A027 | Electrical Feeder Cable Laying - South Section | Electrical | 2026-09-12 | 2026-09-19 | 8 | F06-A017 | Completed | 100 | 96 | m | INFRA-06 | synthetic_demo_data
F06-A028 | Structural Steel Structure Erection - Zone C | Structural | 2026-09-18 | 2026-09-24 | 7 | F06-A004 | Not Started | 100 | 0 | m | INFRA-06 | synthetic_demo_data
F06-A029 | Quality Pavement Thickness Verification - South Section | Quality | 2026-09-06 | 2026-09-17 | 12 | F06-A021 | In Progress | 100 | 80 | m² | INFRA-06 | synthetic_demo_data
F06-A030 | Landscaping Topsoil Placement - Package 2 | Landscaping | 2026-08-14 | 2026-08-21 | 8 | F06-A003 | Not Started | 100 | 0 | m³ | INFRA-06 | synthetic_demo_data

## Data_Dictionary
field | description
activity_id | Unique activity ID
activity_name | Activity name
category | Work category
planned_start | Planned start date
planned_end | Planned finish date
planned_duration_days | Planned duration in days
predecessor | Predecessor activity ID
status | Current schedule status
planned_quantity_percent | Planned completion percentage
current_actual_percent | Current actual completion percentage
unit | Quantity unit
project_id | Synthetic project ID
data_type | Dataset marker