## Schedule
activity_id | activity_name | category | planned_start | planned_end | planned_duration_days | predecessor | status | planned_quantity_percent | current_actual_percent | unit | project_id | data_type
F07-A001 | Drainage Manhole Construction - South Section | Drainage | 2026-09-10 | 2026-09-13 | 4 | — | In Progress | 100 | 52 | m | INFRA-07 | synthetic_demo_data
F07-A002 | Foundation Anchor Bolt Installation - Phase 2 | Foundation | 2026-09-17 | 2026-09-30 | 14 | F07-A001 | In Progress | 100 | 17 | Nos | INFRA-07 | synthetic_demo_data
F07-A003 | Structural Column Reinforcement - Phase 1 | Structural | 2026-08-27 | 2026-09-01 | 6 | F07-A002 | Not Started | 100 | 0 | m | INFRA-07 | synthetic_demo_data
F07-A004 | Electrical Panel Functional Testing - West Section | Electrical | 2026-09-08 | 2026-09-19 | 12 | F07-A001 | Not Started | 100 | 0 | Nos | INFRA-07 | synthetic_demo_data
F07-A005 | Road Asphalt Patching - Zone C | Road | 2026-08-22 | 2026-08-26 | 5 | F07-A001 | Completed | 100 | 97 | m | INFRA-07 | synthetic_demo_data
F07-A006 | Foundation Pile Cage Installation - South Section | Foundation | 2026-09-05 | 2026-09-17 | 13 | F07-A002 | In Progress | 100 | 69 | Nos | INFRA-07 | synthetic_demo_data
F07-A007 | Demolition Existing Pavement Removal - Phase 1 | Demolition | 2026-08-26 | 2026-09-05 | 11 | F07-A003 | Completed | 100 | 97 | m² | INFRA-07 | synthetic_demo_data
F07-A008 | Drainage RCC Drain Construction - Phase 3 | Drainage | 2026-09-04 | 2026-09-16 | 13 | F07-A002 | In Progress | 100 | 33 | m | INFRA-07 | synthetic_demo_data
F07-A009 | Road Thermoplastic Marking - Chainage 500-1000 | Road | 2026-08-30 | 2026-09-06 | 8 | F07-A006 | In Progress | 100 | 40 | m | INFRA-07 | synthetic_demo_data
F07-A010 | Site Survey - Package 1 | Site | 2026-08-30 | 2026-09-05 | 7 | F07-A007 | In Progress | 100 | 53 | Nos | INFRA-07 | synthetic_demo_data
F07-A011 | Structural Beam Concreting - Package 2 | Structural | 2026-09-10 | 2026-09-17 | 8 | F07-A007 | Not Started | 100 | 0 | m³ | INFRA-07 | synthetic_demo_data
F07-A012 | Quality Pavement Thickness Verification - Phase 2 | Quality | 2026-08-29 | 2026-09-08 | 11 | F07-A001 | Completed | 100 | 97 | m² | INFRA-07 | synthetic_demo_data
F07-A013 | Safety Traffic Diversion - Zone A | Safety | 2026-09-16 | 2026-09-27 | 12 | F07-A003 | At Risk | 100 | 67 | m | INFRA-07 | synthetic_demo_data
F07-A014 | Finishing Internal Plaster Finishing - West Section | Finishing | 2026-09-01 | 2026-09-11 | 11 | F07-A013 | In Progress | 100 | 87 | m² | INFRA-07 | synthetic_demo_data
F07-A015 | Road Footpath PCC - Zone A | Road | 2026-09-09 | 2026-09-21 | 13 | F07-A003 | Not Started | 100 | 0 | m³ | INFRA-07 | synthetic_demo_data
F07-A016 | Utility Sewer Pipeline Trenching - Chainage 500-1000 | Utility | 2026-09-16 | 2026-09-27 | 12 | F07-A001 | Not Started | 100 | 0 | m | INFRA-07 | synthetic_demo_data
F07-A017 | Drainage Trench Excavation - Chainage 500-1000 | Drainage | 2026-09-27 | 2026-10-04 | 8 | F07-A016 | At Risk | 100 | 20 | m³ | INFRA-07 | synthetic_demo_data
F07-A018 | Site Temporary Drainage - Chainage 0-500 | Site | 2026-09-05 | 2026-09-13 | 9 | F07-A011 | In Progress | 100 | 45 | m | INFRA-07 | synthetic_demo_data
F07-A019 | Quality Road Level Survey - Zone A | Quality | 2026-09-09 | 2026-09-11 | 3 | F07-A017 | Completed | 100 | 96 | Nos | INFRA-07 | synthetic_demo_data
F07-A020 | Site Temporary Power Supply - South Section | Site | 2026-08-15 | 2026-08-17 | 3 | F07-A005 | In Progress | 100 | 73 | m | INFRA-07 | synthetic_demo_data
F07-A021 | Finishing Floor Tile Installation - Zone B | Finishing | 2026-09-18 | 2026-09-23 | 6 | F07-A010 | Completed | 100 | 97 | Nos | INFRA-07 | synthetic_demo_data
F07-A022 | Road Shoulder Construction - East Section | Road | 2026-08-20 | 2026-08-23 | 4 | F07-A018 | Completed | 100 | 98 | m | INFRA-07 | synthetic_demo_data
F07-A023 | Landscaping Irrigation Line Installation - East Section | Landscaping | 2026-08-29 | 2026-09-08 | 11 | F07-A007 | At Risk | 100 | 58 | Nos | INFRA-07 | synthetic_demo_data
F07-A024 | Landscaping Lawn Preparation - Chainage 500-1000 | Landscaping | 2026-09-04 | 2026-09-10 | 7 | F07-A022 | In Progress | 100 | 90 | m | INFRA-07 | synthetic_demo_data
F07-A025 | Electrical Control Panel Installation - Package 2 | Electrical | 2026-09-14 | 2026-09-17 | 4 | F07-A021 | Completed | 100 | 96 | Nos | INFRA-07 | synthetic_demo_data
F07-A026 | Structural Protective Painting - Zone C | Structural | 2026-09-26 | 2026-10-05 | 10 | F07-A019 | Not Started | 100 | 0 | m² | INFRA-07 | synthetic_demo_data
F07-A027 | Structural Protective Painting - West Section | Structural | 2026-08-21 | 2026-08-26 | 6 | F07-A007 | Completed | 100 | 100 | m² | INFRA-07 | synthetic_demo_data
F07-A028 | Quality Aggregate Gradation Testing - Phase 2 | Quality | 2026-09-01 | 2026-09-06 | 6 | F07-A018 | At Risk | 100 | 74 | Nos | INFRA-07 | synthetic_demo_data
F07-A029 | Utility Water Pipeline Disinfection - Zone C | Utility | 2026-09-15 | 2026-09-15 | 1 | F07-A004 | Completed | 100 | 96 | m | INFRA-07 | synthetic_demo_data
F07-A030 | Road Crash Barrier Installation - North Section | Road | 2026-09-15 | 2026-09-22 | 8 | F07-A029 | At Risk | 100 | 54 | Nos | INFRA-07 | synthetic_demo_data

## Data_Dictionary
field | description
activity_id | Unique activity ID
activity_name | Activity name
category | Work category
planned_start | Planned start date
planned_end | Planned finish date
planned_duration_days | Planned duration in days
predecessor | Predecessor activity ID
status | Current schedule status
planned_quantity_percent | Planned completion percentage
current_actual_percent | Current actual completion percentage
unit | Quantity unit
project_id | Synthetic project ID
data_type | Dataset marker