## Schedule
activity_id | activity_name | category | planned_start | planned_end | planned_duration_days | predecessor | status | planned_quantity_percent | current_actual_percent | unit | project_id | data_type
F09-A001 | Finishing Door Installation - Phase 1 | Finishing | 2026-09-07 | 2026-09-18 | 12 | — | In Progress | 100 | 69 | Nos | INFRA-09 | synthetic_demo_data
F09-A002 | Electrical Streetlight Luminaire Installation - North Section | Electrical | 2026-08-26 | 2026-09-08 | 14 | F09-A001 | Not Started | 100 | 0 | Nos | INFRA-09 | synthetic_demo_data
F09-A003 | Foundation Excavation - Zone B | Foundation | 2026-09-08 | 2026-09-12 | 5 | F09-A001 | In Progress | 100 | 56 | m³ | INFRA-09 | synthetic_demo_data
F09-A004 | Quality Concrete Slump Testing - Package 2 | Quality | 2026-09-01 | 2026-09-10 | 10 | F09-A001 | Completed | 100 | 99 | Nos | INFRA-09 | synthetic_demo_data
F09-A005 | Drainage Outfall Protection - South Section | Drainage | 2026-08-24 | 2026-08-29 | 6 | F09-A002 | In Progress | 100 | 87 | m | INFRA-09 | synthetic_demo_data
F09-A006 | Electrical Streetlight Luminaire Installation - Chainage 500-1000 | Electrical | 2026-09-13 | 2026-09-21 | 9 | F09-A002 | In Progress | 100 | 33 | Nos | INFRA-09 | synthetic_demo_data
F09-A007 | Road Dense Bituminous Macadam - Package 1 | Road | 2026-09-08 | 2026-09-19 | 12 | F09-A001 | In Progress | 100 | 46 | m | INFRA-09 | synthetic_demo_data
F09-A008 | Quality Aggregate Gradation Testing - Zone A | Quality | 2026-09-05 | 2026-09-17 | 13 | F09-A006 | Completed | 100 | 99 | Nos | INFRA-09 | synthetic_demo_data
F09-A009 | Structural Structural Bolt Tightening - Phase 2 | Structural | 2026-08-27 | 2026-08-31 | 5 | F09-A007 | In Progress | 100 | 81 | m | INFRA-09 | synthetic_demo_data
F09-A010 | Road Bituminous Concrete Layer - South Section | Road | 2026-09-08 | 2026-09-08 | 1 | F09-A004 | Not Started | 100 | 0 | m | INFRA-09 | synthetic_demo_data
F09-A011 | Utility Water Pressure Testing - Zone C | Utility | 2026-08-30 | 2026-09-11 | 13 | F09-A006 | Not Started | 100 | 0 | Nos | INFRA-09 | synthetic_demo_data
F09-A012 | Foundation Pedestal Formwork - Zone B | Foundation | 2026-09-20 | 2026-09-25 | 6 | F09-A002 | Completed | 100 | 96 | m | INFRA-09 | synthetic_demo_data
F09-A013 | Site Security Cabin Setup - Package 1 | Site | 2026-09-21 | 2026-10-04 | 14 | F09-A010 | Not Started | 100 | 0 | Nos | INFRA-09 | synthetic_demo_data
F09-A014 | Structural Beam Formwork - Chainage 500-1000 | Structural | 2026-08-21 | 2026-08-22 | 2 | F09-A006 | Not Started | 100 | 0 | m | INFRA-09 | synthetic_demo_data
F09-A015 | Utility Utility Duct Installation - Phase 1 | Utility | 2026-10-01 | 2026-10-07 | 7 | F09-A001 | In Progress | 100 | 19 | Nos | INFRA-09 | synthetic_demo_data
F09-A016 | Foundation PCC - North Section | Foundation | 2026-08-21 | 2026-09-03 | 14 | F09-A010 | In Progress | 100 | 30 | m³ | INFRA-09 | synthetic_demo_data
F09-A017 | Earthwork Selected Fill Placement - Phase 1 | Earthwork | 2026-09-26 | 2026-09-28 | 3 | F09-A003 | In Progress | 100 | 48 | m | INFRA-09 | synthetic_demo_data
F09-A018 | Utility Water Pipeline Laying - North Section | Utility | 2026-09-30 | 2026-10-06 | 7 | F09-A017 | In Progress | 100 | 45 | m | INFRA-09 | synthetic_demo_data
F09-A019 | Road Tack Coat Application - Zone C | Road | 2026-08-27 | 2026-09-04 | 9 | F09-A011 | Completed | 100 | 99 | m | INFRA-09 | synthetic_demo_data
F09-A020 | Utility Shifting Coordination - North Section | Utility | 2026-08-26 | 2026-09-08 | 14 | F09-A004 | Not Started | 100 | 0 | m | INFRA-09 | synthetic_demo_data
F09-A021 | Utility Water Valve Chamber Construction - Package 3 | Utility | 2026-09-21 | 2026-09-23 | 3 | F09-A018 | Completed | 100 | 96 | m | INFRA-09 | synthetic_demo_data
F09-A022 | Utility Crossing Protection - Zone C | Utility | 2026-09-23 | 2026-10-04 | 12 | F09-A015 | In Progress | 100 | 50 | m | INFRA-09 | synthetic_demo_data
F09-A023 | Utility Stormwater Pipeline Laying - South Section | Utility | 2026-09-06 | 2026-09-11 | 6 | F09-A019 | Not Started | 100 | 0 | m | INFRA-09 | synthetic_demo_data
F09-A024 | Utility Marker Installation - North Section | Utility | 2026-08-21 | 2026-08-30 | 10 | F09-A016 | In Progress | 100 | 47 | Nos | INFRA-09 | synthetic_demo_data
F09-A025 | Electrical Lightning Protection - Phase 1 | Electrical | 2026-08-21 | 2026-09-01 | 12 | F09-A012 | At Risk | 100 | 71 | m | INFRA-09 | synthetic_demo_data
F09-A026 | Drainage Culvert Construction - Phase 3 | Drainage | 2026-09-13 | 2026-09-14 | 2 | F09-A016 | In Progress | 100 | 57 | m | INFRA-09 | synthetic_demo_data
F09-A027 | Drainage Culvert Construction - Package 1 | Drainage | 2026-09-07 | 2026-09-08 | 2 | F09-A023 | In Progress | 100 | 63 | m | INFRA-09 | synthetic_demo_data
F09-A028 | Rehabilitation Existing Road Resurfacing - Phase 3 | Rehabilitation | 2026-08-24 | 2026-08-29 | 6 | F09-A019 | In Progress | 100 | 72 | m | INFRA-09 | synthetic_demo_data
F09-A029 | Structural Retaining Wall Concreting - South Section | Structural | 2026-09-10 | 2026-09-20 | 11 | F09-A027 | Completed | 100 | 96 | m³ | INFRA-09 | synthetic_demo_data
F09-A030 | Demolition Existing Kerb Removal - Chainage 500-1000 | Demolition | 2026-09-24 | 2026-09-29 | 6 | F09-A029 | Completed | 100 | 100 | m | INFRA-09 | synthetic_demo_data

## Data_Dictionary
field | description
activity_id | Unique activity ID
activity_name | Activity name
category | Work category
planned_start | Planned start date
planned_end | Planned finish date
planned_duration_days | Planned duration in days
predecessor | Predecessor activity ID
status | Current schedule status
planned_quantity_percent | Planned completion percentage
current_actual_percent | Current actual completion percentage
unit | Quantity unit
project_id | Synthetic project ID
data_type | Dataset marker