## Schedule
activity_id | activity_name | category | planned_start | planned_end | planned_duration_days | predecessor | status | planned_quantity_percent | current_actual_percent | unit | project_id | data_type
F10-A001 | Structural Steel Member Fabrication - East Section | Structural | 2026-08-30 | 2026-09-11 | 13 | — | Not Started | 100 | 0 | m | INFRA-10 | synthetic_demo_data
F10-A002 | Rehabilitation Existing Culvert Rehabilitation - Phase 2 | Rehabilitation | 2026-09-10 | 2026-09-23 | 14 | F10-A001 | Completed | 100 | 97 | m | INFRA-10 | synthetic_demo_data
F10-A003 | Finishing Metal Railing Installation - Zone C | Finishing | 2026-10-04 | 2026-10-11 | 8 | F10-A002 | Completed | 100 | 96 | Nos | INFRA-10 | synthetic_demo_data
F10-A004 | Finishing Waterproofing Membrane - Zone A | Finishing | 2026-09-25 | 2026-09-27 | 3 | F10-A001 | Completed | 100 | 96 | m² | INFRA-10 | synthetic_demo_data
F10-A005 | Earthwork Grading - North Section | Earthwork | 2026-09-04 | 2026-09-17 | 14 | F10-A002 | In Progress | 100 | 31 | m² | INFRA-10 | synthetic_demo_data
F10-A006 | Utility Sewer Pipeline Laying - Package 1 | Utility | 2026-09-07 | 2026-09-18 | 12 | F10-A004 | In Progress | 100 | 25 | m | INFRA-10 | synthetic_demo_data
F10-A007 | Quality Final Work Inspection - West Section | Quality | 2026-08-25 | 2026-08-31 | 7 | F10-A003 | At Risk | 100 | 38 | Nos | INFRA-10 | synthetic_demo_data
F10-A008 | Structural Column Formwork - Package 2 | Structural | 2026-09-07 | 2026-09-14 | 8 | F10-A005 | In Progress | 100 | 36 | m | INFRA-10 | synthetic_demo_data
F10-A009 | Structural Steel Structure Erection - Zone B | Structural | 2026-08-22 | 2026-08-22 | 1 | F10-A008 | Not Started | 100 | 0 | m | INFRA-10 | synthetic_demo_data
F10-A010 | Finishing Wall Tile Installation - Zone B | Finishing | 2026-09-02 | 2026-09-15 | 14 | F10-A001 | Not Started | 100 | 0 | Nos | INFRA-10 | synthetic_demo_data
F10-A011 | Site Security Cabin Setup - Chainage 500-1000 | Site | 2026-08-24 | 2026-08-25 | 2 | F10-A003 | In Progress | 100 | 18 | Nos | INFRA-10 | synthetic_demo_data
F10-A012 | Utility Service Connection - West Section | Utility | 2026-08-23 | 2026-09-01 | 10 | F10-A009 | In Progress | 100 | 73 | m | INFRA-10 | synthetic_demo_data
F10-A013 | Demolition Existing Structure Demolition - Phase 1 | Demolition | 2026-09-02 | 2026-09-04 | 3 | F10-A001 | Completed | 100 | 98 | m | INFRA-10 | synthetic_demo_data
F10-A014 | Utility Sewer Pipeline Laying - Package 2 | Utility | 2026-08-24 | 2026-09-05 | 13 | F10-A007 | Completed | 100 | 99 | m | INFRA-10 | synthetic_demo_data
F10-A015 | Finishing Sealant Application - Phase 1 | Finishing | 2026-09-05 | 2026-09-15 | 11 | F10-A012 | In Progress | 100 | 65 | m | INFRA-10 | synthetic_demo_data
F10-A016 | Earthwork Final Level Preparation - Phase 3 | Earthwork | 2026-09-18 | 2026-09-28 | 11 | F10-A013 | In Progress | 100 | 47 | m | INFRA-10 | synthetic_demo_data
F10-A017 | Quality Pre-Construction Inspection - West Section | Quality | 2026-09-02 | 2026-09-10 | 9 | F10-A008 | Not Started | 100 | 0 | Nos | INFRA-10 | synthetic_demo_data
F10-A018 | Utility Stormwater Pipeline Laying - Zone C | Utility | 2026-10-05 | 2026-10-17 | 13 | F10-A013 | In Progress | 100 | 41 | m | INFRA-10 | synthetic_demo_data
F10-A019 | Road Crash Barrier Installation - Chainage 500-1000 | Road | 2026-09-03 | 2026-09-07 | 5 | F10-A005 | At Risk | 100 | 64 | Nos | INFRA-10 | synthetic_demo_data
F10-A020 | Utility Sewer Line Relocation - Zone C | Utility | 2026-09-14 | 2026-09-22 | 9 | F10-A009 | At Risk | 100 | 72 | m | INFRA-10 | synthetic_demo_data
F10-A021 | Foundation PCC - East Section | Foundation | 2026-09-12 | 2026-09-24 | 13 | F10-A019 | In Progress | 100 | 30 | m³ | INFRA-10 | synthetic_demo_data
F10-A022 | Road Tack Coat Application - Zone B | Road | 2026-09-08 | 2026-09-15 | 8 | F10-A016 | In Progress | 100 | 15 | m | INFRA-10 | synthetic_demo_data
F10-A023 | Rehabilitation Concrete Rehabilitation - Phase 1 | Rehabilitation | 2026-09-02 | 2026-09-07 | 6 | F10-A007 | In Progress | 100 | 78 | m | INFRA-10 | synthetic_demo_data
F10-A024 | Utility Stormwater Pipeline Laying - Phase 2 | Utility | 2026-09-25 | 2026-10-03 | 9 | F10-A001 | In Progress | 100 | 18 | m | INFRA-10 | synthetic_demo_data
F10-A025 | Utility Sewer Line Relocation - Package 3 | Utility | 2026-09-08 | 2026-09-15 | 8 | F10-A002 | At Risk | 100 | 30 | m | INFRA-10 | synthetic_demo_data
F10-A026 | Drainage Pipe Joint Testing - Zone B | Drainage | 2026-09-27 | 2026-10-07 | 11 | F10-A005 | In Progress | 100 | 23 | Nos | INFRA-10 | synthetic_demo_data
F10-A027 | Drainage Pipe Joint Testing - Phase 1 | Drainage | 2026-09-15 | 2026-09-26 | 12 | F10-A003 | In Progress | 100 | 85 | Nos | INFRA-10 | synthetic_demo_data
F10-A028 | Utility Shifting Coordination - Chainage 500-1000 | Utility | 2026-08-29 | 2026-08-31 | 3 | F10-A026 | In Progress | 100 | 31 | m | INFRA-10 | synthetic_demo_data
F10-A029 | Earthwork Surplus Soil Disposal - Phase 2 | Earthwork | 2026-09-03 | 2026-09-15 | 13 | F10-A024 | In Progress | 100 | 47 | m³ | INFRA-10 | synthetic_demo_data
F10-A030 | Utility Sewer Line Relocation - South Section | Utility | 2026-09-26 | 2026-10-02 | 7 | F10-A026 | In Progress | 100 | 16 | m | INFRA-10 | synthetic_demo_data

## Data_Dictionary
field | description
activity_id | Unique activity ID
activity_name | Activity name
category | Work category
planned_start | Planned start date
planned_end | Planned finish date
planned_duration_days | Planned duration in days
predecessor | Predecessor activity ID
status | Current schedule status
planned_quantity_percent | Planned completion percentage
current_actual_percent | Current actual completion percentage
unit | Quantity unit
project_id | Synthetic project ID
data_type | Dataset marker