## Schedule
activity_id | activity_name | category | planned_start | planned_end | planned_duration_days | predecessor | status | planned_quantity_percent | current_actual_percent | unit | project_id | data_type
F05-A001 | Road Kerb Laying - Zone B | Road | 2026-08-24 | 2026-09-06 | 14 | — | Not Started | 100 | 0 | m | INFRA-05 | synthetic_demo_data
F05-A002 | Quality Workfront Handover Inspection - North Section | Quality | 2026-08-14 | 2026-08-27 | 14 | F05-A001 | In Progress | 100 | 61 | Nos | INFRA-05 | synthetic_demo_data
F05-A003 | Utility Utility Chamber Construction - Phase 2 | Utility | 2026-09-23 | 2026-10-06 | 14 | F05-A001 | In Progress | 100 | 37 | m | INFRA-05 | synthetic_demo_data
F05-A004 | Site Access Road Construction - Zone A | Site | 2026-08-21 | 2026-09-01 | 12 | F05-A003 | In Progress | 100 | 44 | m | INFRA-05 | synthetic_demo_data
F05-A005 | Finishing Metal Railing Installation - East Section | Finishing | 2026-08-29 | 2026-09-10 | 13 | F05-A002 | Completed | 100 | 96 | Nos | INFRA-05 | synthetic_demo_data
F05-A006 | Quality Pavement Thickness Verification - Package 1 | Quality | 2026-08-26 | 2026-09-07 | 13 | F05-A003 | In Progress | 100 | 53 | m² | INFRA-05 | synthetic_demo_data
F05-A007 | Rehabilitation Existing Road Resurfacing - East Section | Rehabilitation | 2026-08-24 | 2026-08-27 | 4 | F05-A003 | Completed | 100 | 96 | m | INFRA-05 | synthetic_demo_data
F05-A008 | Foundation Backfilling - Phase 2 | Foundation | 2026-09-06 | 2026-09-14 | 9 | F05-A001 | In Progress | 100 | 45 | m³ | INFRA-05 | synthetic_demo_data
F05-A009 | Structural Column Reinforcement - Phase 2 | Structural | 2026-09-18 | 2026-09-22 | 5 | F05-A007 | Not Started | 100 | 0 | m | INFRA-05 | synthetic_demo_data
F05-A010 | Finishing Kerb Painting - Chainage 500-1000 | Finishing | 2026-09-18 | 2026-09-20 | 3 | F05-A009 | In Progress | 100 | 26 | m² | INFRA-05 | synthetic_demo_data
F05-A011 | Road Delineator Installation - Phase 1 | Road | 2026-09-07 | 2026-09-12 | 6 | F05-A008 | Not Started | 100 | 0 | Nos | INFRA-05 | synthetic_demo_data
F05-A012 | Finishing Road Furniture Painting - East Section | Finishing | 2026-08-29 | 2026-09-11 | 14 | F05-A010 | In Progress | 100 | 85 | m² | INFRA-05 | synthetic_demo_data
F05-A013 | Road Kerb Laying - Zone C | Road | 2026-09-16 | 2026-09-18 | 3 | F05-A009 | In Progress | 100 | 84 | m | INFRA-05 | synthetic_demo_data
F05-A014 | Road Asphalt Patching - East Section | Road | 2026-08-14 | 2026-08-19 | 6 | F05-A007 | In Progress | 100 | 81 | m | INFRA-05 | synthetic_demo_data
F05-A015 | Quality Material Inspection - Chainage 500-1000 | Quality | 2026-09-01 | 2026-09-04 | 4 | F05-A007 | In Progress | 100 | 87 | Nos | INFRA-05 | synthetic_demo_data
F05-A016 | Road Paver Block Installation - Phase 1 | Road | 2026-08-29 | 2026-09-02 | 5 | F05-A010 | Completed | 100 | 99 | Nos | INFRA-05 | synthetic_demo_data
F05-A017 | Finishing Final Cleaning - Package 3 | Finishing | 2026-08-14 | 2026-08-21 | 8 | F05-A001 | In Progress | 100 | 78 | m | INFRA-05 | synthetic_demo_data
F05-A018 | Electrical Feeder Cable Laying - Phase 3 | Electrical | 2026-08-24 | 2026-09-04 | 12 | F05-A011 | Not Started | 100 | 0 | m | INFRA-05 | synthetic_demo_data
F05-A019 | Road Road Marking - Zone A | Road | 2026-09-01 | 2026-09-10 | 10 | F05-A009 | In Progress | 100 | 65 | m | INFRA-05 | synthetic_demo_data
F05-A020 | Earthwork Haulage - Package 3 | Earthwork | 2026-08-23 | 2026-08-26 | 4 | F05-A018 | Completed | 100 | 98 | m | INFRA-05 | synthetic_demo_data
F05-A021 | Foundation Pile Bore Excavation - Phase 3 | Foundation | 2026-09-05 | 2026-09-17 | 13 | F05-A017 | In Progress | 100 | 49 | m³ | INFRA-05 | synthetic_demo_data
F05-A022 | Landscaping Shrub Plantation - South Section | Landscaping | 2026-08-13 | 2026-08-17 | 5 | F05-A012 | At Risk | 100 | 24 | Nos | INFRA-05 | synthetic_demo_data
F05-A023 | Road Shoulder Construction - Chainage 0-500 | Road | 2026-09-12 | 2026-09-23 | 12 | F05-A016 | In Progress | 100 | 90 | m | INFRA-05 | synthetic_demo_data
F05-A024 | Road Reflector Installation - Chainage 0-500 | Road | 2026-08-21 | 2026-08-23 | 3 | F05-A021 | In Progress | 100 | 58 | Nos | INFRA-05 | synthetic_demo_data
F05-A025 | Site Temporary Drainage - Package 2 | Site | 2026-09-25 | 2026-10-05 | 11 | F05-A005 | At Risk | 100 | 27 | m | INFRA-05 | synthetic_demo_data
F05-A026 | Earthwork Excavation - Phase 2 | Earthwork | 2026-09-23 | 2026-09-24 | 2 | F05-A005 | In Progress | 100 | 29 | m³ | INFRA-05 | synthetic_demo_data
F05-A027 | Utility Water Pipeline Trenching - Phase 3 | Utility | 2026-09-02 | 2026-09-11 | 10 | F05-A007 | In Progress | 100 | 35 | m | INFRA-05 | synthetic_demo_data
F05-A028 | Road Guardrail Installation - Zone C | Road | 2026-08-16 | 2026-08-24 | 9 | F05-A016 | In Progress | 100 | 86 | Nos | INFRA-05 | synthetic_demo_data
F05-A029 | Foundation Pile Bore Excavation - Package 2 | Foundation | 2026-09-05 | 2026-09-06 | 2 | F05-A024 | In Progress | 100 | 64 | m³ | INFRA-05 | synthetic_demo_data
F05-A030 | Drainage Chamber Waterproofing - Zone C | Drainage | 2026-09-15 | 2026-09-17 | 3 | F05-A016 | Not Started | 100 | 0 | m² | INFRA-05 | synthetic_demo_data

## Data_Dictionary
field | description
activity_id | Unique activity ID
activity_name | Activity name
category | Work category
planned_start | Planned start date
planned_end | Planned finish date
planned_duration_days | Planned duration in days
predecessor | Predecessor activity ID
status | Current schedule status
planned_quantity_percent | Planned completion percentage
current_actual_percent | Current actual completion percentage
unit | Quantity unit
project_id | Synthetic project ID
data_type | Dataset marker