## Schedule
activity_id | activity_name | category | planned_start | planned_end | planned_duration_days | predecessor | status | planned_quantity_percent | current_actual_percent | unit | project_id | data_type
F08-A001 | Finishing Final Cleaning - Phase 3 | Finishing | 2026-08-21 | 2026-08-28 | 8 | — | In Progress | 100 | 29 | m | INFRA-08 | synthetic_demo_data
F08-A002 | Site Security Cabin Setup - East Section | Site | 2026-10-01 | 2026-10-05 | 5 | F08-A001 | Completed | 100 | 97 | Nos | INFRA-08 | synthetic_demo_data
F08-A003 | Finishing Internal Plaster Finishing - Package 2 | Finishing | 2026-09-15 | 2026-09-21 | 7 | F08-A001 | Not Started | 100 | 0 | m² | INFRA-08 | synthetic_demo_data
F08-A004 | Structural Beam Formwork - Zone A | Structural | 2026-09-02 | 2026-09-07 | 6 | F08-A001 | In Progress | 100 | 80 | m | INFRA-08 | synthetic_demo_data
F08-A005 | Demolition Existing Fence Removal - Phase 2 | Demolition | 2026-09-18 | 2026-09-22 | 5 | F08-A004 | In Progress | 100 | 76 | m | INFRA-08 | synthetic_demo_data
F08-A006 | Road Subgrade Preparation - Phase 3 | Road | 2026-08-30 | 2026-09-07 | 9 | F08-A002 | In Progress | 100 | 86 | m | INFRA-08 | synthetic_demo_data
F08-A007 | Site Access Road Construction - Phase 3 | Site | 2026-09-11 | 2026-09-20 | 10 | F08-A001 | At Risk | 100 | 58 | m | INFRA-08 | synthetic_demo_data
F08-A008 | Structural Column Reinforcement - South Section | Structural | 2026-08-26 | 2026-08-31 | 6 | F08-A001 | In Progress | 100 | 70 | m | INFRA-08 | synthetic_demo_data
F08-A009 | Utility Stormwater Pipeline Laying - North Section | Utility | 2026-09-21 | 2026-09-24 | 4 | F08-A004 | Completed | 100 | 98 | m | INFRA-08 | synthetic_demo_data
F08-A010 | Finishing Wall Tile Installation - Phase 2 | Finishing | 2026-09-17 | 2026-09-18 | 2 | F08-A008 | In Progress | 100 | 73 | Nos | INFRA-08 | synthetic_demo_data
F08-A011 | Road Delineator Installation - Zone C | Road | 2026-08-22 | 2026-09-01 | 11 | F08-A008 | Completed | 100 | 97 | Nos | INFRA-08 | synthetic_demo_data
F08-A012 | Road Paver Block Installation - North Section | Road | 2026-08-18 | 2026-08-19 | 2 | F08-A002 | In Progress | 100 | 70 | Nos | INFRA-08 | synthetic_demo_data
F08-A013 | Foundation Pedestal Concreting - Chainage 0-500 | Foundation | 2026-09-16 | 2026-09-17 | 2 | F08-A002 | Completed | 100 | 96 | m³ | INFRA-08 | synthetic_demo_data
F08-A014 | Road Asphalt Patching - Zone A | Road | 2026-09-14 | 2026-09-26 | 13 | F08-A003 | At Risk | 100 | 28 | m | INFRA-08 | synthetic_demo_data
F08-A015 | Drainage Desilting - South Section | Drainage | 2026-08-26 | 2026-08-31 | 6 | F08-A014 | In Progress | 100 | 41 | m | INFRA-08 | synthetic_demo_data
F08-A016 | Site Clearance - Phase 2 | Site | 2026-09-12 | 2026-09-13 | 2 | F08-A011 | In Progress | 100 | 45 | m | INFRA-08 | synthetic_demo_data
F08-A017 | Electrical Panel Functional Testing - North Section | Electrical | 2026-08-29 | 2026-09-09 | 12 | F08-A011 | In Progress | 100 | 57 | Nos | INFRA-08 | synthetic_demo_data
F08-A018 | Foundation Pile Bore Excavation - North Section | Foundation | 2026-09-17 | 2026-09-21 | 5 | F08-A003 | Not Started | 100 | 0 | m³ | INFRA-08 | synthetic_demo_data
F08-A019 | Earthwork Soil Replacement - Package 3 | Earthwork | 2026-08-19 | 2026-08-31 | 13 | F08-A013 | Not Started | 100 | 0 | m³ | INFRA-08 | synthetic_demo_data
F08-A020 | Foundation Pile Bore Excavation - South Section | Foundation | 2026-09-14 | 2026-09-16 | 3 | F08-A007 | Not Started | 100 | 0 | m³ | INFRA-08 | synthetic_demo_data
F08-A021 | Drainage Chamber Waterproofing - Package 2 | Drainage | 2026-08-24 | 2026-09-03 | 11 | F08-A013 | Not Started | 100 | 0 | m² | INFRA-08 | synthetic_demo_data
F08-A022 | Quality Drawing Verification - Phase 3 | Quality | 2026-09-05 | 2026-09-17 | 13 | F08-A018 | In Progress | 100 | 48 | m | INFRA-08 | synthetic_demo_data
F08-A023 | Foundation Pile Cage Installation - Package 2 | Foundation | 2026-09-06 | 2026-09-15 | 10 | F08-A010 | In Progress | 100 | 89 | Nos | INFRA-08 | synthetic_demo_data
F08-A024 | Quality Workfront Handover Inspection - Package 2 | Quality | 2026-08-20 | 2026-08-24 | 5 | F08-A002 | Completed | 100 | 98 | Nos | INFRA-08 | synthetic_demo_data
F08-A025 | Rehabilitation Concrete Rehabilitation - Package 3 | Rehabilitation | 2026-08-26 | 2026-08-29 | 4 | F08-A002 | In Progress | 100 | 44 | m | INFRA-08 | synthetic_demo_data
F08-A026 | Electrical Cable Tray Installation - Package 2 | Electrical | 2026-09-24 | 2026-10-06 | 13 | F08-A011 | Not Started | 100 | 0 | Nos | INFRA-08 | synthetic_demo_data
F08-A027 | Structural Beam Concreting - Chainage 0-500 | Structural | 2026-09-19 | 2026-09-26 | 8 | F08-A019 | Not Started | 100 | 0 | m³ | INFRA-08 | synthetic_demo_data
F08-A028 | Site Welfare Facility Setup - Zone C | Site | 2026-08-31 | 2026-09-11 | 12 | F08-A024 | Completed | 100 | 96 | m | INFRA-08 | synthetic_demo_data
F08-A029 | Site Temporary Lighting - East Section | Site | 2026-08-26 | 2026-08-31 | 6 | F08-A020 | Not Started | 100 | 0 | m | INFRA-08 | synthetic_demo_data
F08-A030 | Structural Surface Repair - South Section | Structural | 2026-09-26 | 2026-10-08 | 13 | F08-A015 | At Risk | 100 | 63 | m² | INFRA-08 | synthetic_demo_data

## Data_Dictionary
field | description
activity_id | Unique activity ID
activity_name | Activity name
category | Work category
planned_start | Planned start date
planned_end | Planned finish date
planned_duration_days | Planned duration in days
predecessor | Predecessor activity ID
status | Current schedule status
planned_quantity_percent | Planned completion percentage
current_actual_percent | Current actual completion percentage
unit | Quantity unit
project_id | Synthetic project ID
data_type | Dataset marker